## Sheet1
Phase | Task | Notes | Critical Uncertainty / Block | Assignee
Pre-processing | Exclusion rules |  |  | ? HF
| Join post-analysis survey and round 2 survey together |  | Need a unique ID column, not guaranteed to match on Team Name or other column | ? HF
| Format predictions files |  | Incorrectly formatted files | TP
| Formatting of joined surveys |  | What inputs do we need for the meta-analysis? | HF first-pass, others to check
| Process review surveys |  | What processing is required, see requirements in meta-analysis | ? EG
Compute raw values for meta-analysis | Compute Zr, first Derive r corelation coefficient | extract t value | Can compute t values
|  | assign r sign | Not sure if we can do automatically, might need to be manually coded? | can probably just look at t values or slope. Tim to code direction, flag for SN to follow up
| Compute Zr | derive r from t and df and convert r to Zr |  | EG
| Point Estimates | Transform all values to original scale, inc standard errors, delta method for transformation of SE. | We need a rule for back-transforming each different method | SN to obtain the mathematical rules for each link function transformation. EG to provide complete list to SN and to code up SN's functions
Meta-analysis | Forest plots
Random Effects Meta-Analysis
GLMs on Box-Cox transformed deviation scores - A
GLMs on Box-Cox transformed deviation scores - B
Sorensen's Similarity Index vs. Deviation Scores
Univariate analysis
Multi-variate analysis