## Sheet1
| 2021 |  |  |  |  | 2022 | [11 empty] | 2023
Chapter | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
4 - Preregistration for Ecological Modelling | Complete Preregistration of CJ analysis. |  | Write Discussion. Revise MS. | Submit pre-print & peer-review
5 - Many EcoEvo Specification Curve Analysis | Many EcoEvo Project Data analysis |  | SCA - Modelling & Data Analysis |  |  |  | Draft Manuscript |  | Submit pre-print & peer-review
2 - Reproducibility and Transparency SysReview | [7 empty] | Formulate analysis plan |  | Execute analysis plan |  |  | Draft Manuscript |  | Submit pre-print & peer-review
3 - QRP Roadmaps |  |  |  |  | Update Roadmap Figure | Revise Draft | Submit Pre-print and peer-review
1 - Update Lit Review | [14 empty] | Update Literature Review |  | Revise Draft | Supervisor Feedback
Thesis Introducttion | [18 empty] | Write, send to supervisors |  |  | Edit & Respond to Feedback
Thesis Discussion | [19 empty] | Write, send to supervisors |  |  | Edit & Respond to Feedback
Editing and Formatting
Binding and Submission